## Daily_Fact
Sütun1 | Report Date | KKK | Project | Sütun2 | Type of Work | Sub Type of Work | Sub Sub Type of Work | Fact Quantity | Unit | Type of Code | Fact Manday | Submitted By | Sütun22 | Sütun23 | Sütun24 | Crew | Head of Masters | Crew Region | Project Manager | Site Chief | Sütun19 | Sütun20 | Sütun21 | ZZZ | Sütun3 | Sütun4 | Sütun5 | Sütun6 | Sütun7 | Sütun8 | Sütun9 | Sütun10 | Sütun11 | Sütun12 | Sütun13 | Sütun14 | Sütun15 | Sütun16 | Sütun17 | Sütun18
|  | 30DDD | AAA.0199.30DDD.0.KK.TZ0006 |  | TOW-02 | STOW-23 | SSTOW-77 | 3.92 | t | AAA0201042026 | 31 | bbolgetechoffice@icn.com |  |  |  | Rebar Fixer | 30DDD-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60114402
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-17 | STOW-155 | SSTOW-455 | -1 | m3 | AAA90022026 | 2 | abolgetechoffice@icn.com |  |  |  | General Labor | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-15 | STOW-147 | SSTOW-412 | -1 | - | AAA20022026 | 0 | abolgetechoffice@icn.com |  |  |  | Operators | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-16 | STOW-150 | SSTOW-415 | -1 | t | AAA20032026 | 0 | abolgetechoffice@icn.com |  |  |  | Operators | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-15 | STOW-147 | SSTOW-412 | -1 | - | AAA20022026 | -1 | abolgetechoffice@icn.com |  |  |  | Operators | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-22 | STOW-173 | SSTOW-474 | -1 | - | AAA9405022026 | 3 | abolgetechoffice@icn.com |  |  |  | Survey | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-22 | STOW-173 | SSTOW-473 | -1 | - | AAA9405012026 | 1 | bbolgetechoffice@icn.com |  |  |  | Survey | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30BBB | AAA.0199.30BBB.0.KK.TZ0004 |  | TOW-15 | STOW-146 | SSTOW-411 | -1 | - | AAA20012026 | 1 | abolgetechoffice@icn.com |  |  |  | Survey | 30BBB-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-15 | STOW-146 | SSTOW-411 | -1 | - | AAA20012026 | -1 | abolgetechoffice@icn.com |  |  |  | Operators | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30BBB | AAA.0199.30BBB.0.KK.TZ0004 |  | TOW-16 | STOW-151 | SSTOW-416 | -1 | - | AAA20072026 | -1 | abolgetechoffice@icn.com |  |  |  | Operators | 30BBB-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-16 | STOW-151 | SSTOW-416 | -1 | - | AAA20072026 | 0 | abolgetechoffice@icn.com |  |  |  | Slinger | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-17 | STOW-154 | SSTOW-453 | -1 | m2 | AAA9001082026 | 0 | abolgetechoffice@icn.com |  |  |  | Slinger | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-04 | SSTOW-27 | 49 | m2 | AAA0104012026 | 1 | abolgetechoffice@icn.com |  |  |  | Formworker | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-01 | STOW-04 | SSTOW-27 | 4 | m2 | AAA0104012026 | 0 | abolgetechoffice@icn.com |  |  |  | Architectural Worker | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-01 | STOW-10 | SSTOW-35 | 4 | m2 | AAA01052026 | 0 | abolgetechoffice@icn.com |  |  |  | Architectural Worker | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-10 | SSTOW-35 | 4 | m2 | AAA01052026 | 1 | abolgetechoffice@icn.com |  |  |  | Formworker | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-01 | STOW-13 | SSTOW-48 | 4 | m2 | AAA0108052026 | 1 | bbolgetechoffice@icn.com |  |  |  | Formworker | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30FFF | AAA.0199.30FFF.0.KK.TZ0024 |  | TOW-02 | STOW-23 | SSTOW-77 | 4 | t | AAA0201042026 | 1 | bbolgetechoffice@icn.com |  |  |  | Formworker | 30FFF-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60114402
|  | 99UUU | 0001_Unproductive Works |  | TOW-21 | STOW-168 | SSTOW-468 | 29 | - | AAA93012026 | 4 | bbolgetechoffice@icn.com |  |  |  | Formworker | 99UUU-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30DDD | AAA.0199.30DDD.0.KK.TZ0006 |  | TOW-02 | STOW-25 | SSTOW-83 | 3.92 | t | AAA02042026 | 31 | bbolgetechoffice@icn.com |  |  |  | Rebar Fixer | 30DDD-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-12 | SSTOW-41 | 0.797 | m2 | AAA0107052026 | 26 | abolgetechoffice@icn.com |  |  |  | Rebar Fixer | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-01 | STOW-10 | SSTOW-35 | -1 | m2 | AAA01052026 | 2 | bbolgetechoffice@icn.com |  |  |  | Rebar Fixer | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-03 | STOW-51 | SSTOW-146 | -1 | t | AAA0303072026 | 5 | abolgetechoffice@icn.com |  |  |  | Rebar Fixer | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 60101508
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-03 | STOW-51 | SSTOW-146 | 9 | t | AAA0303072026 | 14 | abolgetechoffice@icn.com |  |  |  | Formworker | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 60101508
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-03 | STOW-51 | SSTOW-148 | 9 | t | AAA0303082026 | 12 | bbolgetechoffice@icn.com |  |  |  | Formworker | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60101509
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-03 | STOW-41 | SSTOW-129 | 9 | t | AAA0306052026 | 9 | abolgetechoffice@icn.com |  |  |  | Formworker | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-03 | STOW-41 | SSTOW-129 | -0.892 | t | AAA0306052026 | 10 | bbolgetechoffice@icn.com |  |  |  | Assembler | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0

## Daily_Report
Sütun1 | Report Date | KKK | Project | Sütun2 | Type of Work | Sub Type of Work | Sub Sub Type of Work | Planned Quantity | Unit | Type of Code | Planned Manday | Submitted By | Fact Quantity | Fact Manday | Effiency | Crew | Head of Masters | Crew Region | Project Manager | Site Chief | Sütun19 | Sütun20 | Sütun21 | ZZZ | Sütun3 | Sütun4 | Sütun5 | Sütun6 | Sütun7 | Sütun8 | Sütun9 | Sütun10 | Sütun11 | Sütun12 | Sütun13 | Sütun14 | Sütun15 | Sütun16 | Sütun17 | Sütun18
|  | 30DDD | AAA.0199.30DDD.0.KK.TZ0006 |  | TOW-02 | STOW-23 | SSTOW-77 | 4.92 | t | AAA0201042026 | 33 | bbolgetechoffice@icn.com | 3.92 | 31 |  | Rebar Fixer | 30DDD-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60114402
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-17 | STOW-155 | SSTOW-455 | 0 | m3 | AAA90022026 | 4 | abolgetechoffice@icn.com | -1 | 2 |  | General Labor | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-15 | STOW-147 | SSTOW-412 | 0 | - | AAA20022026 | 2 | abolgetechoffice@icn.com | -1 | 0 |  | Operators | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-16 | STOW-150 | SSTOW-415 | 0 | t | AAA20032026 | 2 | abolgetechoffice@icn.com | -1 | 0 |  | Operators | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-15 | STOW-147 | SSTOW-412 | 0 | - | AAA20022026 | 1 | abolgetechoffice@icn.com | -1 | -1 |  | Operators | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-22 | STOW-173 | SSTOW-474 | 0 | - | AAA9405022026 | 5 | abolgetechoffice@icn.com | -1 | 3 |  | Survey | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-22 | STOW-173 | SSTOW-473 | 0 | - | AAA9405012026 | 3 | bbolgetechoffice@icn.com | -1 | 1 |  | Survey | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30BBB | AAA.0199.30BBB.0.KK.TZ0004 |  | TOW-15 | STOW-146 | SSTOW-411 | 0 | - | AAA20012026 | 3 | abolgetechoffice@icn.com | -1 | 1 |  | Survey | 30BBB-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-15 | STOW-146 | SSTOW-411 | 0 | - | AAA20012026 | 1 | abolgetechoffice@icn.com | -1 | -1 |  | Operators | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30BBB | AAA.0199.30BBB.0.KK.TZ0004 |  | TOW-16 | STOW-151 | SSTOW-416 | 0 | - | AAA20072026 | 1 | abolgetechoffice@icn.com | -1 | -1 |  | Operators | 30BBB-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-16 | STOW-151 | SSTOW-416 | 0 | - | AAA20072026 | 2 | abolgetechoffice@icn.com | -1 | 0 |  | Slinger | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-17 | STOW-154 | SSTOW-453 | 0 | m2 | AAA9001082026 | 2 | abolgetechoffice@icn.com | -1 | 0 |  | Slinger | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-04 | SSTOW-27 | 50 | m2 | AAA0104012026 | 3 | abolgetechoffice@icn.com | 49 | 1 |  | Formworker | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-01 | STOW-04 | SSTOW-27 | 5 | m2 | AAA0104012026 | 2 | abolgetechoffice@icn.com | 4 | 0 |  | Architectural Worker | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-01 | STOW-10 | SSTOW-35 | 5 | m2 | AAA01052026 | 2 | abolgetechoffice@icn.com | 4 | 0 |  | Architectural Worker | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-10 | SSTOW-35 | 5 | m2 | AAA01052026 | 3 | abolgetechoffice@icn.com | 4 | 1 |  | Formworker | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-01 | STOW-13 | SSTOW-48 | 5 | m2 | AAA0108052026 | 3 | bbolgetechoffice@icn.com | 4 | 1 |  | Formworker | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30FFF | AAA.0199.30FFF.0.KK.TZ0024 |  | TOW-02 | STOW-23 | SSTOW-77 | 5 | t | AAA0201042026 | 3 | bbolgetechoffice@icn.com | 4 | 1 |  | Formworker | 30FFF-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60114402
|  | 99UUU | 0001_Unproductive Works |  | TOW-21 | STOW-168 | SSTOW-468 | 30 | - | AAA93012026 | 6 | bbolgetechoffice@icn.com | 29 | 4 |  | Formworker | 99UUU-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30DDD | AAA.0199.30DDD.0.KK.TZ0006 |  | TOW-02 | STOW-25 | SSTOW-83 | 4.92 | t | AAA02042026 | 33 | bbolgetechoffice@icn.com | 3.92 | 31 |  | Rebar Fixer | 30DDD-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-12 | SSTOW-41 | 1.797 | m2 | AAA0107052026 | 28 | abolgetechoffice@icn.com | 0.797 | 26 |  | Rebar Fixer | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-01 | STOW-10 | SSTOW-35 | 0 | m2 | AAA01052026 | 4 | bbolgetechoffice@icn.com | -1 | 2 |  | Rebar Fixer | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-03 | STOW-51 | SSTOW-146 | 0 | t | AAA0303072026 | 7 | abolgetechoffice@icn.com | -1 | 5 |  | Rebar Fixer | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 60101508
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-03 | STOW-51 | SSTOW-146 | 10 | t | AAA0303072026 | 16 | abolgetechoffice@icn.com | 9 | 14 |  | Formworker | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 60101508
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-03 | STOW-51 | SSTOW-148 | 10 | t | AAA0303082026 | 14 | bbolgetechoffice@icn.com | 9 | 12 |  | Formworker | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60101509
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-03 | STOW-41 | SSTOW-129 | 10 | t | AAA0306052026 | 11 | abolgetechoffice@icn.com | 9 | 9 |  | Formworker | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-03 | STOW-41 | SSTOW-129 | 0.108 | t | AAA0306052026 | 12 | bbolgetechoffice@icn.com | -0.892 | 10 |  | Assembler | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0

## Daily_Plan
Sütun1 | Report Date | KKK | Project | Sütun2 | Type of Work | Sub Type of Work | Sub Sub Type of Work | Planned Quantity | Unit | Type of Code | Planned Manday | Submitted By | Sütun22 | Sütun23 | Sütun24 | Crew | Head of Masters | Crew Region | Project Manager | Site Chief | Sütun19 | Sütun20 | Sütun21 | ZZZ | Sütun3 | Sütun4 | Sütun5 | Sütun6 | Sütun7 | Sütun8 | Sütun9 | Sütun10 | Sütun11 | Sütun12 | Sütun13 | Sütun14 | Sütun15 | Sütun16 | Sütun17 | Sütun18
|  | 30DDD | AAA.0199.30DDD.0.KK.TZ0006 |  | TOW-02 | STOW-23 | SSTOW-77 | 4.92 | t | AAA0201042026 | 33 | bbolgetechoffice@icn.com |  |  |  |  | 30DDD-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60114402
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-17 | STOW-155 | SSTOW-455 | 0 | m3 | AAA90022026 | 4 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-15 | STOW-147 | SSTOW-412 | 0 | - | AAA20022026 | 2 | abolgetechoffice@icn.com |  |  |  |  | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-16 | STOW-150 | SSTOW-415 | 0 | t | AAA20032026 | 2 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-15 | STOW-147 | SSTOW-412 | 0 | - | AAA20022026 | 1 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-22 | STOW-173 | SSTOW-474 | 0 | - | AAA9405022026 | 5 | abolgetechoffice@icn.com |  |  |  |  | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-22 | STOW-173 | SSTOW-473 | 0 | - | AAA9405012026 | 3 | bbolgetechoffice@icn.com |  |  |  |  | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30BBB | AAA.0199.30BBB.0.KK.TZ0004 |  | TOW-15 | STOW-146 | SSTOW-411 | 0 | - | AAA20012026 | 3 | abolgetechoffice@icn.com |  |  |  |  | 30BBB-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-15 | STOW-146 | SSTOW-411 | 0 | - | AAA20012026 | 1 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30BBB | AAA.0199.30BBB.0.KK.TZ0004 |  | TOW-16 | STOW-151 | SSTOW-416 | 0 | - | AAA20072026 | 1 | abolgetechoffice@icn.com |  |  |  |  | 30BBB-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-16 | STOW-151 | SSTOW-416 | 0 | - | AAA20072026 | 2 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-17 | STOW-154 | SSTOW-453 | 0 | m2 | AAA9001082026 | 2 | abolgetechoffice@icn.com |  |  |  |  | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-04 | SSTOW-27 | 50 | m2 | AAA0104012026 | 3 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-01 | STOW-04 | SSTOW-27 | 5 | m2 | AAA0104012026 | 2 | abolgetechoffice@icn.com |  |  |  |  | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-01 | STOW-10 | SSTOW-35 | 5 | m2 | AAA01052026 | 2 | abolgetechoffice@icn.com |  |  |  |  | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-10 | SSTOW-35 | 5 | m2 | AAA01052026 | 3 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-01 | STOW-13 | SSTOW-48 | 5 | m2 | AAA0108052026 | 3 | bbolgetechoffice@icn.com |  |  |  |  | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30FFF | AAA.0199.30FFF.0.KK.TZ0024 |  | TOW-02 | STOW-23 | SSTOW-77 | 5 | t | AAA0201042026 | 3 | bbolgetechoffice@icn.com |  |  |  |  | 30FFF-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60114402
|  | 99UUU | 0001_Unproductive Works |  | TOW-21 | STOW-168 | SSTOW-468 | 30 | - | AAA93012026 | 6 | bbolgetechoffice@icn.com |  |  |  |  | 99UUU-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30DDD | AAA.0199.30DDD.0.KK.TZ0006 |  | TOW-02 | STOW-25 | SSTOW-83 | 4.92 | t | AAA02042026 | 33 | bbolgetechoffice@icn.com |  |  |  |  | 30DDD-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-01 | STOW-12 | SSTOW-41 | 1.797 | m2 | AAA0107052026 | 28 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-01 | STOW-10 | SSTOW-35 | 0 | m2 | AAA01052026 | 4 | bbolgetechoffice@icn.com |  |  |  |  | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-03 | STOW-51 | SSTOW-146 | 0 | t | AAA0303072026 | 7 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 60101508
|  | 30CCC | AAA.0199.30CCC.0.KK.TZ0005 |  | TOW-03 | STOW-51 | SSTOW-146 | 10 | t | AAA0303072026 | 16 | abolgetechoffice@icn.com |  |  |  |  | 30CCC-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 60101508
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-03 | STOW-51 | SSTOW-148 | 10 | t | AAA0303082026 | 14 | bbolgetechoffice@icn.com |  |  |  |  | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 60101509
|  | 30AAA | AAA.0199.30AAA.0.KK.TZ0003 |  | TOW-03 | STOW-41 | SSTOW-129 | 10 | t | AAA0306052026 | 11 | abolgetechoffice@icn.com |  |  |  |  | 30AAA-hom@icn.com | abolge | pm@icn.com | abolge_sc@icn.com |  |  |  | 0
|  | 30EEE | AAA.0199.30EEE.0.KK.TZ0023 |  | TOW-03 | STOW-41 | SSTOW-129 | 0.108 | t | AAA0306052026 | 12 | bbolgetechoffice@icn.com |  |  |  |  | 30EEE-hom@icn.com | bbolge | pm@icn.com | bbolge_sc@icn.com |  |  |  | 0

## Detay
60114402
N/A
60101508
60101509

## Lokasyon
30DDD
30AAA
30CCC
30EEE
30BBB
30FFF
99UUU

## worker
Rebar Fixer
General Labor
Operators
Survey
Slinger
Formworker
Architectural Worker
Assembler
Welder

## Sub_Type
Type of Works | Sub Type of Works | Sub Sub Type of Works | Unit | Type of Code |  | ZZZ
TOW-01 | STOW-01 | SSTOW-01 | m3 | AAA01002026 |  | 60100101
TOW-01 | STOW-01 | SSTOW-02 | m3 | AAA0101012026 |  | 60114604
TOW-01 | STOW-01 | SSTOW-03 | m3 | AAA0101022026 |  | 60114403
TOW-01 | STOW-01 | SSTOW-04 | m3 | AAA0101032026 |  | 60114404
TOW-01 | STOW-01 | SSTOW-05 | m3 | AAA0101042026 |  | 60114405
TOW-01 | STOW-01 | SSTOW-06 | m3 | AAA0101052026 |  | 60114706
TOW-01 | STOW-01 | SSTOW-07 | m3 | AAA0101062026 |  | 60114705
TOW-01 | STOW-01 | SSTOW-08 | m3 | AAA0101072026 |  | 60114707
TOW-01 | STOW-01 | SSTOW-09 | m3 | AAA0101082026
TOW-01 | STOW-01 | SSTOW-10 | m3 | AAA0101092026 |  | 60114503
TOW-01 | STOW-01 | SSTOW-11 | m3 | AAA0101102026 |  | 60114504
TOW-01 | STOW-01 | SSTOW-12 | m3 | AAA0101132026 |  | 060114503K
TOW-01 | STOW-01 | SSTOW-13 | m3 | AAA0101142026 |  | 060114504K
TOW-01 | STOW-01 | SSTOW-14 | m3 | AAA010109012026 |  | 60114505
TOW-01 | STOW-01 | SSTOW-15 | m3 | AAA010110012026 |  | 60114506
TOW-01 | STOW-01 | SSTOW-16 | m3 | AAA010113012026 |  | 060114505K
TOW-01 | STOW-01 | SSTOW-17 | m3 | AAA010114012026 |  | 060114506K
TOW-01 | STOW-01 | SSTOW-18 | m3 | AAA0101112026 |  | 110101101
TOW-01 | STOW-01 | SSTOW-19 | m3 | AAA0101122026
TOW-01 | STOW-01 | SSTOW-20 | m3 | AAA0101152026
TOW-01 | STOW-01 | SSTOW-21 | m3 | AAA0101162026
TOW-01 | STOW-01 | SSTOW-22 | m3 | AAA0101172026 |  | 110100209
TOW-01 | STOW-02 | SSTOW-23 | m3 | AAA0101992026
TOW-01 | STOW-03 | SSTOW-24 | m3 | AAA01022026 |  | 350147301
TOW-01 | STOW-03 | SSTOW-25 | m3 | AAA0102012026 |  | 420100802
TOW-01 | STOW-03 | SSTOW-26 | m3 | AAA0102022026
TOW-01 | STOW-04 | SSTOW-27 | m2 | AAA0104012026
TOW-01 | STOW-04 | SSTOW-28 | m2 | AAA0104022026 |  | 130600301
TOW-01 | STOW-04 | SSTOW-29 | m2 | AAA0104032026
TOW-01 | STOW-05 | SSTOW-30 | m | AAA01162026
TOW-01 | STOW-06 | SSTOW-31 | m3 | AAA01172026
TOW-01 | STOW-07 | SSTOW-32 | pcs | AAA01192026
TOW-01 | STOW-08 | SSTOW-33 | pcs | AAA01182026
TOW-01 | STOW-09 | SSTOW-34 | m2 | AAA01042026
TOW-01 | STOW-10 | SSTOW-35 | m2 | AAA01052026
TOW-01 | STOW-11 | SSTOW-36 | m3 | AAA01062026
TOW-01 | STOW-12 | SSTOW-37 | m2 | AAA0107012026
TOW-01 | STOW-12 | SSTOW-38 | m2 | AAA0107022026
TOW-01 | STOW-12 | SSTOW-39 | m2 | AAA0107032026
TOW-01 | STOW-12 | SSTOW-40 | m2 | AAA0107042026
TOW-01 | STOW-12 | SSTOW-41 | m2 | AAA0107052026
TOW-01 | STOW-12 | SSTOW-42 | m2 | AAA0107062026
TOW-01 | STOW-12 | SSTOW-43 | m2 | AAA0107072026
TOW-01 | STOW-13 | SSTOW-44 | m2 | AAA0108012026
TOW-01 | STOW-13 | SSTOW-45 | m2 | AAA0108022026
TOW-01 | STOW-13 | SSTOW-46 | m2 | AAA0108032026
TOW-01 | STOW-13 | SSTOW-47 | m2 | AAA0108042026
TOW-01 | STOW-13 | SSTOW-48 | m2 | AAA0108052026
TOW-01 | STOW-13 | SSTOW-49 | m2 | AAA0108062026
TOW-01 | STOW-13 | SSTOW-50 | m2 | AAA0108072026
TOW-01 | STOW-14 | SSTOW-51 | m2 | AAA0109012026
TOW-01 | STOW-15 | SSTOW-52 | m2 | AAA0109022026
TOW-01 | STOW-16 | SSTOW-53 | m3 | AAA01102026
TOW-01 | STOW-17 | SSTOW-54 | m2 | AAA01112026
TOW-01 | STOW-17 | SSTOW-55 | m2 | AAA0111012026
TOW-01 | STOW-17 | SSTOW-56 | m2 | AAA0111022026
TOW-01 | STOW-17 | SSTOW-57 | m2 | AAA0111032026
TOW-01 | STOW-17 | SSTOW-58 | m2 | AAA0111042026
TOW-01 | STOW-17 | SSTOW-59 | m2 | AAA0111052026
TOW-01 | STOW-17 | SSTOW-60 | m2 | AAA0111122026
TOW-01 | STOW-17 | SSTOW-61 | m2 | AAA0111062026
TOW-01 | STOW-17 | SSTOW-62 | m2 | AAA0111072026
TOW-01 | STOW-17 | SSTOW-63 | m2 | AAA0111082026
TOW-01 | STOW-17 | SSTOW-64 | m2 | AAA0111092026
TOW-01 | STOW-17 | SSTOW-65 | m2 | AAA0111102026
TOW-01 | STOW-17 | SSTOW-66 | m2 | AAA0111112026
TOW-01 | STOW-17 | SSTOW-67 | m2 | AAA0111132026
TOW-01 | STOW-18 | SSTOW-68 | pcs | AAA01122026
TOW-01 | STOW-19 | SSTOW-69 | m3 | AAA01132026 |  | 440206504
TOW-01 | STOW-19 | SSTOW-70 | m3 | AAA0113012026
TOW-01 | STOW-20 | SSTOW-71 | pcs | AAA01202026
TOW-01 | STOW-21 | SSTOW-72 | m3 | AAA01212026
TOW-01 | STOW-22 | SSTOW-73 | m3 | AAA01222026 |  | 370400108
TOW-02 | STOW-23 | SSTOW-74 | t | AAA0201012026 |  | 60114602
TOW-02 | STOW-23 | SSTOW-75 | t | AAA0201022026 |  | 60114502
TOW-02 | STOW-23 | SSTOW-76 | t | AAA0201032026
TOW-02 | STOW-23 | SSTOW-77 | t | AAA0201042026 |  | 60114402
TOW-02 | STOW-23 | SSTOW-78 | t | AAA0201052026 |  | 60114701
TOW-02 | STOW-24 | SSTOW-79 | t | AAA0201062026
TOW-02 | STOW-23 | SSTOW-80 | t | AAA0201102026
TOW-02 | STOW-23 | SSTOW-81 | t | AAA0201112026
TOW-02 | STOW-23 | SSTOW-82 | t | AAA0201122026
TOW-02 | STOW-25 | SSTOW-83 | t | AAA02042026
TOW-02 | STOW-26 | SSTOW-84 | t | AAA0201072026
TOW-02 | STOW-27 | SSTOW-85 | pcs | AAA0205012026
TOW-02 | STOW-28 | SSTOW-86 | pcs | AAA0205022026
TOW-02 | STOW-29 | SSTOW-87 | pcs | AAA02062026
TOW-02 | STOW-30 | SSTOW-88 | pcs | AAA02112026
TOW-02 | STOW-31 | SSTOW-89 | pcs | AAA02072026
TOW-02 | STOW-32 | SSTOW-90 | t | AAA0208012026 |  | 370102701
TOW-02 | STOW-32 | SSTOW-91 | t | AAA0208022026 |  | 370102702
TOW-02 | STOW-32 | SSTOW-92 | t | AAA0208032026 |  | 370102703
TOW-02 | STOW-33 | SSTOW-93 | t | AAA0208052026 |  | 60109201
TOW-02 | STOW-33 | SSTOW-94 | t | AAA0208062026 |  | 60109202
TOW-02 | STOW-33 | SSTOW-95 | t | AAA0208072026 |  | 60109203
TOW-02 | STOW-33 | SSTOW-96 | t | AAA0208082026 |  | 60109204
TOW-02 | STOW-33 | SSTOW-97 | t | AAA0208092026 |  | 60109205
TOW-02 | STOW-33 | SSTOW-98 | t | AAA0208102026
TOW-02 | STOW-33 | SSTOW-99 | t | AAA0208112026 |  | 60109206
TOW-02 | STOW-34 | SSTOW-100 | t | AAA0208042026
TOW-02 | STOW-23 | SSTOW-101 | t | AAA0210012026
TOW-02 | STOW-23 | SSTOW-102 | t | AAA0201082026
TOW-02 | STOW-23 | SSTOW-103 | t | AAA0201092026
TOW-02 | STOW-35 | SSTOW-104 | t | AAA02092026
TOW-02 | STOW-36 | SSTOW-105 | m2 | AAA02102026 |  | 270600901
TOW-03 | STOW-37 | SSTOW-106 | t | AAA0301012026 |  | 90201903
TOW-03 | STOW-38 | SSTOW-107 | t | AAA0301022026 |  | 90303001
TOW-03 | STOW-37 | SSTOW-108 | t | AAA0301032026 |  | 90201802
TOW-03 | STOW-37 | SSTOW-109 | t | AAA0301042026 |  | 90300211
TOW-03 | STOW-37 | SSTOW-110 | t | AAA0301052026 |  | 90300212
TOW-03 | STOW-37 | SSTOW-111 | t | AAA0301062026 |  | 90301201
TOW-03 | STOW-37 | SSTOW-112 | t | AAA030106012026 |  | 90301203
TOW-03 | STOW-37 | SSTOW-113 | t | AAA0301072026 |  | 90301401
TOW-03 | STOW-37 | SSTOW-114 | t | AAA0301082026 |  | 90301402
TOW-03 | STOW-37 | SSTOW-115 | t | AAA0301092026 |  | 90301501
TOW-03 | STOW-37 | SSTOW-116 | t | AAA0301132026 |  | 90301502
TOW-03 | STOW-37 | SSTOW-117 | t | AAA0301122026 |  | 90301302
TOW-03 | STOW-39 | SSTOW-118 | t | AAA0302012026
TOW-03 | STOW-38 | SSTOW-119 | t | AAA0301102026 |  | 90303901
TOW-03 | STOW-37 | SSTOW-120 | t | AAA0301112026 |  | 90100602
TOW-03 | STOW-40 | SSTOW-121 | t | AAA03042026 |  | 220101112
TOW-03 | STOW-40 | SSTOW-122 | t | AAA0304012026 |  | 390100401
TOW-03 | STOW-40 | SSTOW-123 | m | AAA030401022026
TOW-03 | STOW-40 | SSTOW-124 | t | AAA0304022026 |  | 60101506
TOW-03 | STOW-38 | SSTOW-125 | t | AAA03052026
TOW-03 | STOW-41 | SSTOW-126 | t | AAA0306012026
TOW-03 | STOW-41 | SSTOW-127 | pcs | AAA0306022026
TOW-03 | STOW-41 | SSTOW-128 | pcs | AAA0306032026
TOW-03 | STOW-41 | SSTOW-129 | t | AAA0306052026
TOW-03 | STOW-42 | SSTOW-130 | t | AAA0307012026 |  | 90700401
TOW-03 | STOW-42 | SSTOW-131 | t | AAA0307022026 |  | 90700402
TOW-03 | STOW-42 | SSTOW-132 | t | AAA0307032026
TOW-03 | STOW-42 | SSTOW-133 | t | AAA0307042026 |  | 90700301
TOW-03 | STOW-43 | SSTOW-134 | pcs | AAA03082026
TOW-03 | STOW-44 | SSTOW-135 | t | AAA03132026
TOW-03 | STOW-45 | SSTOW-136 | m2 | AAA03092026
TOW-03 | STOW-46 | SSTOW-137 | m2 | AAA03102026
TOW-03 | STOW-47 | SSTOW-138 | m2 | AAA03112026
TOW-03 | STOW-38 | SSTOW-139 | t | AAA03122026
TOW-03 | STOW-38 | SSTOW-140 | t | AAA0312012026 |  | 90302901
TOW-03 | STOW-48 | SSTOW-141 | t | AAA03142026
TOW-03 | STOW-49 | SSTOW-142 | t | AAA03022026
TOW-03 | STOW-50 | SSTOW-143 | t | AAA03992026
TOW-03 | STOW-51 | SSTOW-144 | t | AAA0303012026 |  | 60101507
TOW-03 | STOW-51 | SSTOW-145 | t | AAA0303022026 |  | 60101508
TOW-03 | STOW-51 | SSTOW-146 | t | AAA0303072026 |  | 60101508
TOW-03 | STOW-51 | SSTOW-147 | t | AAA0303032026 |  | 60101509
TOW-03 | STOW-51 | SSTOW-148 | t | AAA0303082026 |  | 60101509
TOW-03 | STOW-51 | SSTOW-149 | t | AAA0303132026
TOW-03 | STOW-51 | SSTOW-150 | t | AAA0303142026
TOW-03 | STOW-51 | SSTOW-151 | t | AAA0303152026
TOW-03 | STOW-51 | SSTOW-152 | t | AAA0303162026
TOW-03 | STOW-51 | SSTOW-153 | t | AAA0303172026
TOW-03 | STOW-52 | SSTOW-154 | t | AAA0303042026
TOW-03 | STOW-52 | SSTOW-155 | t | AAA0303052026
TOW-03 | STOW-52 | SSTOW-156 | t | AAA0303092026
TOW-03 | STOW-52 | SSTOW-157 | t | AAA0303062026
TOW-03 | STOW-52 | SSTOW-158 | t | AAA0303102026
TOW-03 | STOW-53 | SSTOW-159 | t | AAA0303112026
TOW-03 | STOW-54 | SSTOW-160 | t | AAA0303122026
TOW-04 | STOW-55 | SSTOW-161 | m3 | AAA04012026 |  | 10101204
TOW-04 | STOW-56 | SSTOW-162 | m3 | AAA04022026
TOW-04 | STOW-57 | SSTOW-163 | m3 | AAA04142026 |  | 10205701
TOW-04 | STOW-58 | SSTOW-164 | m3 | AAA04032026
TOW-04 | STOW-59 | SSTOW-165 | m3 | AAA04042026
TOW-04 | STOW-60 | SSTOW-166 | m3 | AAA0405012026 |  | 60107002
TOW-04 | STOW-60 | SSTOW-167 | m3 | AAA0405022026 |  | 10103702
TOW-04 | STOW-60 | SSTOW-168 | m3 | AAA0405032026 |  | 10104603
TOW-04 | STOW-60 | SSTOW-169 | m3 | AAA0405042026 |  | 10104401
TOW-04 | STOW-61 | SSTOW-170 | m3 | AAA04062026
TOW-04 | STOW-62 | SSTOW-171 | m3 | AAA04132026 |  | 10206102
TOW-04 | STOW-63 | SSTOW-172 | m3 | AAA04072026
TOW-04 | STOW-64 | SSTOW-173 | m3 | AAA0408012026 |  | 10200105
TOW-04 | STOW-64 | SSTOW-174 | m3 | AAA0408022026 |  | 10200502
TOW-04 | STOW-65 | SSTOW-175 | m3 | AAA04092026
TOW-04 | STOW-66 | SSTOW-176 | m2 | AAA0412012026
TOW-04 | STOW-67 | SSTOW-177 | m2 | AAA0412022026
TOW-04 | STOW-68 | SSTOW-178 | m2 | AAA0412032026
TOW-04 | STOW-69 | SSTOW-179 | m2 | AAA0412042026
TOW-04 | STOW-70 | SSTOW-180 | m3 | AAA04162026
TOW-04 | STOW-71 | SSTOW-181 | m2 | AAA04152026 |  | 10202703
TOW-04 | STOW-71 | SSTOW-182 | m2 | AAA0415012026 |  | 10110902
TOW-04 | STOW-72 | SSTOW-183 | m3 | AAA04172026 |  | 380201311
TOW-04 | STOW-73 | SSTOW-184 | m3 | AAA04182026 |  | 230100102
TOW-04 | STOW-74 | SSTOW-185 | m3 | AAA04192026 |  | 10209401
TOW-05 | STOW-75 | SSTOW-186 | m3 | AAA05012026
TOW-05 | STOW-76 | SSTOW-187 | m | AAA05022026
TOW-05 | STOW-77 | SSTOW-188 | pcs | AAA05032026
TOW-05 | STOW-78 | SSTOW-189 | m3 | AAA05042026
TOW-05 | STOW-79 | SSTOW-190 | m3 | AAA05052026
TOW-05 | STOW-80 | SSTOW-191 | t | AAA05072026
TOW-06 | STOW-81 | SSTOW-192 | m3 | AAA06012026
TOW-06 | STOW-82 | SSTOW-193 | m2 | AAA06022026 |  | 270401604
TOW-06 | STOW-83 | SSTOW-194 | m2 | AAA06032026 |  | 27 0602006
TOW-06 | STOW-84 | SSTOW-195 | pcs | AAA06042026
TOW-06 | STOW-85 | SSTOW-196 | pcs | AAA06052026 |  | 270900801
TOW-06 | STOW-86 | SSTOW-197 | m2 | AAA06112026 |  | 270600217
TOW-06 | STOW-86 | SSTOW-198 | m3 | AAA06122026 |  | 10101504
TOW-06 | STOW-87 | SSTOW-199 | m | AAA06132026 |  | 270900205
TOW-07 | STOW-88 | SSTOW-200 | m | AAA0606012026
TOW-07 | STOW-88 | SSTOW-201 | m | AAA0606022026
TOW-07 | STOW-88 | SSTOW-202 | m | AAA0606032026
TOW-07 | STOW-88 | SSTOW-203 | m | AAA0606042026
TOW-07 | STOW-88 | SSTOW-204 | m | AAA0606052026
TOW-07 | STOW-88 | SSTOW-205 | m | AAA0606062026
TOW-07 | STOW-88 | SSTOW-206 | m | AAA0606072026
TOW-07 | STOW-88 | SSTOW-207 | m | AAA0606082026
TOW-07 | STOW-88 | SSTOW-208 | m | AAA0607012026
TOW-07 | STOW-88 | SSTOW-209 | m | AAA0607022026
TOW-07 | STOW-88 | SSTOW-210 | m | AAA0607032026
TOW-07 | STOW-88 | SSTOW-211 | m | AAA0607042026
TOW-07 | STOW-88 | SSTOW-212 | m | AAA0607052026
TOW-07 | STOW-88 | SSTOW-213 | m | AAA0607062026
TOW-07 | STOW-88 | SSTOW-214 | m | AAA0607072026
TOW-07 | STOW-88 | SSTOW-215 | m | AAA0607082026
TOW-07 | STOW-88 | SSTOW-216 | m | AAA0607092026
TOW-07 | STOW-88 | SSTOW-217 | m | AAA0607102026
TOW-07 | STOW-88 | SSTOW-218 | m | AAA0607112026
TOW-07 | STOW-88 | SSTOW-219 | m | AAA0607122026
TOW-07 | STOW-88 | SSTOW-220 | m | AAA0607132026
TOW-07 | STOW-88 | SSTOW-221 | m | AAA0607142026
TOW-07 | STOW-88 | SSTOW-222 | m | AAA0608012026
TOW-07 | STOW-88 | SSTOW-223 | m | AAA0608022026
TOW-07 | STOW-88 | SSTOW-224 | m | AAA0608032026
TOW-07 | STOW-88 | SSTOW-225 | m | AAA0608042026
TOW-07 | STOW-88 | SSTOW-226 | m | AAA0608052026
TOW-07 | STOW-88 | SSTOW-227 | m | AAA0608062026
TOW-07 | STOW-88 | SSTOW-228 | m | AAA0608072026
TOW-07 | STOW-88 | SSTOW-229 | m | AAA0608082026
TOW-07 | STOW-88 | SSTOW-230 | m | AAA0608092026
TOW-07 | STOW-88 | SSTOW-231 | m | AAA0608102026
TOW-07 | STOW-88 | SSTOW-232 | m | AAA0608112026
TOW-07 | STOW-88 | SSTOW-233 | m | AAA0608122026
TOW-07 | STOW-88 | SSTOW-234 | m | AAA0608132026
TOW-07 | STOW-88 | SSTOW-235 | m | AAA0608142026
TOW-07 | STOW-88 | SSTOW-236 | m | AAA0608152026
TOW-07 | STOW-88 | SSTOW-237 | m | AAA0608162026
TOW-07 | STOW-88 | SSTOW-238 | m | AAA0608172026
TOW-07 | STOW-88 | SSTOW-239 | m | AAA0608182026
TOW-07 | STOW-88 | SSTOW-240 | m | AAA0608192026
TOW-07 | STOW-88 | SSTOW-241 | m | AAA0608202026
TOW-07 | STOW-88 | SSTOW-242 | m | AAA0608212026
TOW-07 | STOW-88 | SSTOW-243 | m | AAA0608222026
TOW-07 | STOW-88 | SSTOW-244 | m | AAA0608232026
TOW-07 | STOW-88 | SSTOW-245 | m3 | AAA06192026 |  | 270400101
TOW-07 | STOW-89 | SSTOW-246 | pcs | AAA06172026 |  | 220300501
TOW-07 | STOW-89 | SSTOW-247 | t | AAA06182026 |  | 220300105
TOW-07 | STOW-89 | SSTOW-248 | pcs | AAA0618012026 |  | 220300202
TOW-07 | STOW-89 | SSTOW-249 | pcs | AAA0618022026 |  | 220300201
TOW-07 | STOW-90 | SSTOW-250 | t | AAA06202026
TOW-07 | STOW-91 | SSTOW-251 | m3 | AAA06102026
TOW-08 | STOW-92 | SSTOW-252 | m2 | AAA07012026 |  | 260105703
TOW-08 | STOW-93 | SSTOW-253 | m2 | AAA07022026 |  | 80100307
TOW-08 | STOW-94 | SSTOW-254 | m2 | AAA0702012026 |  | 130300102
TOW-08 | STOW-95 | SSTOW-255 | m2 | AAA07132026 |  | 130300601
TOW-08 | STOW-96 | SSTOW-256 | m2 | AAA07032026
TOW-08 | STOW-97 | SSTOW-257 | m2 | AAA07042026 |  | 120102101
TOW-08 | STOW-97 | SSTOW-258 | m2 | AAA0704012026
TOW-08 | STOW-97 | SSTOW-259 | m2 | AAA0704022026
TOW-08 | STOW-97 | SSTOW-260 | m2 | AAA0704032026
TOW-08 | STOW-97 | SSTOW-261 | m2 | AAA0704042026
TOW-08 | STOW-98 | SSTOW-262 | m | AAA07052026
TOW-08 | STOW-99 | SSTOW-263 | m2 | AAA07062026
TOW-08 | STOW-100 | SSTOW-264 | m2 | AAA07072026
TOW-08 | STOW-101 | SSTOW-265 | m2 | AAA07082026
TOW-08 | STOW-102 | SSTOW-266 | m2 | AAA0701012026
TOW-08 | STOW-103 | SSTOW-267 | m2 | AAA07092026 |  | 130300601
TOW-08 | STOW-104 | SSTOW-268 | m | AAA07102026
TOW-08 | STOW-105 | SSTOW-269 | m2 | AAA07112026
TOW-08 | STOW-106 | SSTOW-270 | m3 | AAA07122026
TOW-09 | STOW-107 | SSTOW-271 | m2 | AAA08012026 | Ceramic Floor Coverings
TOW-09 | STOW-108 | SSTOW-272 | m2 | AAA08182026 | Ceramic Wall Coverings
TOW-09 | STOW-109 | SSTOW-273 | m | AAA08192026 | 0
TOW-09 | STOW-110 | SSTOW-274 | m2 | AAA08022026 | PVC Floor Coverings
TOW-09 | STOW-111 | SSTOW-275 | m2 | AAA08032026 | Wooden Floor Coverings
TOW-09 | STOW-112 | SSTOW-276 | m2 | AAA08042026 | Epoxy Floor Coverings
TOW-09 | STOW-113 | SSTOW-277 | m2 | AAA08052026 | Wall Coverings
TOW-09 | STOW-114 | SSTOW-278 | m2 | AAA08062026 | Cement Based Plaster Works
TOW-09 | STOW-114 | SSTOW-279 | m2 | AAA08152026 | Satin Plaster Works (m2) | 150201903
TOW-09 | STOW-114 | SSTOW-280 | m2 | AAA08162026 | Satin Plaster Works (m2)
TOW-09 | STOW-115 | SSTOW-281 | m | AAA08172026 | 0
TOW-09 | STOW-116 | SSTOW-282 | m2 | AAA0807012026 | Painting Works (1 Coat) (m2) | 150400701
TOW-09 | STOW-116 | SSTOW-283 | m2 | AAA0807022026 | Painting Works (1 Coat) (m2) | 150400701
TOW-09 | STOW-116 | SSTOW-284 | m2 | AAA0807032026 | Painting Works (1 Coat) (m2) | 150400701
TOW-09 | STOW-116 | SSTOW-285 | m2 | AAA0807042026 | Painting Works (1 Coat) (m2) | 150400701
TOW-09 | STOW-117 | SSTOW-286 | m2 | AAA08082026 | Ceiling Coverings
TOW-09 | STOW-118 | SSTOW-287 | m3 | AAA08092026
TOW-09 | STOW-119 | SSTOW-288 | m3 | AAA0809012026
TOW-09 | STOW-120 | SSTOW-289 | pcs | AAA08102026 | 0
TOW-09 | STOW-121 | SSTOW-290 | pcs | AAA08112026 | 0
TOW-10 | STOW-122 | SSTOW-291 | m2 | AAA12012026
TOW-10 | STOW-122 | SSTOW-292 | m | AAA1201012026
TOW-10 | STOW-122 | SSTOW-293 | m2 | AAA1201022026
TOW-10 | STOW-122 | SSTOW-294 | m2 | AAA1201032026
TOW-10 | STOW-123 | SSTOW-295 | m2 | AAA12022026
TOW-10 | STOW-124 | SSTOW-296 | m2 | AAA12032026
TOW-11 | STOW-125 | SSTOW-297 | - | AAA08142026
TOW-11 | STOW-126 | SSTOW-298 | m | AAA08202026 |  | 270201001
TOW-11 | STOW-127 | SSTOW-299 | m2 | AAA08212026
TOW-11 | STOW-128 | SSTOW-300 | m | AAA08222026
TOW-11 | STOW-129 | SSTOW-301 | m2 | AAA08232026
TOW-12 | STOW-130 | SSTOW-302 | pcs | AAA09012026
TOW-12 | STOW-130 | SSTOW-303 | pcs | AAA09022026
TOW-12 | STOW-130 | SSTOW-304 | m | AAA09032026
TOW-12 | STOW-130 | SSTOW-305 | pcs | AAA09042026
TOW-12 | STOW-130 | SSTOW-306 | m | AAA09052026
TOW-12 | STOW-130 | SSTOW-307 | set | AAA09442026
TOW-12 | STOW-130 | SSTOW-308 | set | AAA09452026
TOW-12 | STOW-131 | SSTOW-309 | pcs | AAA09062026
TOW-12 | STOW-131 | SSTOW-310 | m | AAA09072026 |  | 1604002
TOW-12 | STOW-131 | SSTOW-311 | pcs | AAA0907012026
TOW-12 | STOW-131 | SSTOW-312 | m2 | AAA0907022026
TOW-12 | STOW-131 | SSTOW-313 | m | AAA0907032026
TOW-12 | STOW-131 | SSTOW-314 | m | AAA0907042026
TOW-12 | STOW-131 | SSTOW-315 | m | AAA0907052026
TOW-12 | STOW-131 | SSTOW-316 | m | AAA0907062026
TOW-12 | STOW-131 | SSTOW-317 | m | AAA0907072026
TOW-12 | STOW-131 | SSTOW-318 | m | AAA0907082026
TOW-12 | STOW-131 | SSTOW-319 | pcs | AAA09082026
TOW-12 | STOW-131 | SSTOW-320 | pcs | AAA09092026
TOW-12 | STOW-131 | SSTOW-321 | m | AAA09102026 |  | 1602005
TOW-12 | STOW-131 | SSTOW-322 | t | AAA0910012026 |  | 1602005
TOW-12 | STOW-131 | SSTOW-323 | pcs | AAA09112026
TOW-12 | STOW-131 | SSTOW-324 | pcs | AAA09122026 |  | 160800102
TOW-12 | STOW-131 | SSTOW-325 | m | AAA09132026
TOW-12 | STOW-131 | SSTOW-326 | pcs | AAA09142026
TOW-12 | STOW-131 | SSTOW-327 | set | AAA09352026
TOW-12 | STOW-131 | SSTOW-328 | set | AAA09362026
TOW-12 | STOW-132 | SSTOW-329 | pcs | AAA09462026
TOW-12 | STOW-132 | SSTOW-330 | pcs | AAA09472026
TOW-12 | STOW-132 | SSTOW-331 | m | AAA09482026
TOW-12 | STOW-132 | SSTOW-332 | m | AAA09492026
TOW-12 | STOW-132 | SSTOW-333 | set | AAA09502026
TOW-12 | STOW-132 | SSTOW-334 | set | AAA09512026
TOW-12 | STOW-133 | SSTOW-335 | m | AAA09152026 |  | 1604002
TOW-12 | STOW-133 | SSTOW-336 | m | AAA09162026
TOW-12 | STOW-133 | SSTOW-337 | pcs | AAA09172026
TOW-12 | STOW-133 | SSTOW-338 | m | AAA09182026
TOW-12 | STOW-133 | SSTOW-339 | pcs | AAA09192026
TOW-12 | STOW-133 | SSTOW-340 | pcs | AAA09202026
TOW-12 | STOW-133 | SSTOW-341 | pcs | AAA09212026
TOW-12 | STOW-133 | SSTOW-342 | set | AAA09372026
TOW-12 | STOW-133 | SSTOW-343 | set | AAA09382026
TOW-12 | STOW-134 | SSTOW-344 | m2 | AAA09222026
TOW-12 | STOW-134 | SSTOW-345 | pcs | AAA09232026
TOW-12 | STOW-134 | SSTOW-346 | pcs | AAA09242026
TOW-12 | STOW-134 | SSTOW-347 | pcs | AAA09252026
TOW-12 | STOW-134 | SSTOW-348 | pcs | AAA09262026
TOW-12 | STOW-134 | SSTOW-349 | set | AAA09272026
TOW-12 | STOW-134 | SSTOW-350 | m2 | AAA09282026
TOW-12 | STOW-134 | SSTOW-351 | m2 | AAA09292026
TOW-12 | STOW-134 | SSTOW-352 | pcs | AAA09302026
TOW-12 | STOW-134 | SSTOW-353 | m | AAA09312026
TOW-12 | STOW-134 | SSTOW-354 | pcs | AAA09322026
TOW-12 | STOW-134 | SSTOW-355 | set | AAA09392026
TOW-12 | STOW-134 | SSTOW-356 | set | AAA09402026
TOW-12 | STOW-135 | SSTOW-357 | m | AAA09412026
TOW-12 | STOW-135 | SSTOW-358 | set | AAA09332026
TOW-12 | STOW-135 | SSTOW-359 | pcs | AAA09342026
TOW-12 | STOW-135 | SSTOW-360 | set | AAA09422026
TOW-12 | STOW-135 | SSTOW-361 | set | AAA09432026
TOW-12 | STOW-136 | SSTOW-362 | - | AAA09982026
TOW-12 | STOW-136 | SSTOW-363 | m2 | AAA0998012026
TOW-12 | STOW-136 | SSTOW-364 | m2 | AAA0998022026
TOW-12 | STOW-136 | SSTOW-365 | pcs | AAA0998032026
TOW-12 | STOW-136 | SSTOW-366 | pcs | AAA0998042026
TOW-12 | STOW-137 | SSTOW-367 | - | AAA09992026
TOW-13 | STOW-138 | SSTOW-368 | m | AAA10012026 |  | 80474401
TOW-13 | STOW-138 | SSTOW-369 | pcs | AAA10022026
TOW-13 | STOW-138 | SSTOW-370 | pcs | AAA10032026
TOW-13 | STOW-138 | SSTOW-371 | pcs | AAA10042026 |  | 80357204
TOW-13 | STOW-138 | SSTOW-372 | m | AAA10052026
TOW-13 | STOW-138 | SSTOW-373 | m | AAA10062026
TOW-13 | STOW-138 | SSTOW-374 | set | AAA10252026
TOW-13 | STOW-138 | SSTOW-375 | set | AAA10262026
TOW-13 | STOW-138 | SSTOW-376 | m | AAA10402026
TOW-13 | STOW-139 | SSTOW-377 | pcs | AAA10072026
TOW-13 | STOW-139 | SSTOW-378 | pcs | AAA10082026 |  | 80357204
TOW-13 | STOW-139 | SSTOW-379 | pcs | AAA10092026 |  | 80359110
TOW-13 | STOW-139 | SSTOW-380 | m | AAA10102026 |  | 80474401
TOW-13 | STOW-139 | SSTOW-381 | pcs | AAA10112026
TOW-13 | STOW-139 | SSTOW-382 | set | AAA10272026
TOW-13 | STOW-139 | SSTOW-383 | set | AAA10282026
TOW-13 | STOW-140 | SSTOW-384 | m | AAA10122026
TOW-13 | STOW-140 | SSTOW-385 | pcs | AAA10132026
TOW-13 | STOW-140 | SSTOW-386 | pcs | AAA10142026
TOW-13 | STOW-140 | SSTOW-387 | pcs | AAA10292026
TOW-13 | STOW-140 | SSTOW-388 | set | AAA10302026
TOW-13 | STOW-140 | SSTOW-389 | set | AAA10312026
TOW-13 | STOW-141 | SSTOW-390 | m | AAA10152026
TOW-13 | STOW-141 | SSTOW-391 | pcs | AAA10162026
TOW-13 | STOW-141 | SSTOW-392 | pcs | AAA10172026
TOW-13 | STOW-141 | SSTOW-393 | set | AAA10322026
TOW-13 | STOW-141 | SSTOW-394 | set | AAA10332026
TOW-13 | STOW-141 | SSTOW-395 | pcs | AAA10342026
TOW-13 | STOW-142 | SSTOW-396 | m | AAA10182026 |  | 80474401
TOW-13 | STOW-142 | SSTOW-397 | pcs | AAA10192026
TOW-13 | STOW-142 | SSTOW-398 | pcs | AAA10352026
TOW-13 | STOW-142 | SSTOW-399 | pcs | AAA10202026
TOW-13 | STOW-142 | SSTOW-400 | set | AAA10362026
TOW-13 | STOW-142 | SSTOW-401 | set | AAA10372026
TOW-13 | STOW-143 | SSTOW-402 | pcs | AAA10222026
TOW-13 | STOW-143 | SSTOW-403 | m | AAA10232026
TOW-13 | STOW-143 | SSTOW-404 | set | AAA10242026
TOW-13 | STOW-143 | SSTOW-405 | set | AAA10382026
TOW-13 | STOW-143 | SSTOW-406 | set | AAA10392026
TOW-13 | STOW-144 | SSTOW-407 | - | AAA10992026
TOW-14 | STOW-145 | SSTOW-408 | - | AAA11012026
TOW-14 | STOW-145 | SSTOW-409 | pcs | AAA11022026
TOW-14 | STOW-145 | SSTOW-410 | m2 | AAA11032026
TOW-15 | STOW-146 | SSTOW-411 | - | AAA20012026
TOW-15 | STOW-147 | SSTOW-412 | - | AAA20022026
TOW-15 | STOW-148 | SSTOW-413 | - | AAA20062026
TOW-15 | STOW-149 | SSTOW-414 | - | AAA20052026
TOW-16 | STOW-150 | SSTOW-415 | t | AAA20032026
TOW-16 | STOW-151 | SSTOW-416 | - | AAA20072026
TOW-16 | STOW-152 | SSTOW-417 | t | AAA20042026
TOW-16 | STOW-152 | SSTOW-418 | t | AAA2004012026
TOW-16 | STOW-152 | SSTOW-419 | t | AAA2004022026
TOW-16 | STOW-152 | SSTOW-420 | t | AAA2004082026
TOW-16 | STOW-152 | SSTOW-421 | t | AAA2004092026
TOW-16 | STOW-152 | SSTOW-422 | t | AAA2004102026
TOW-16 | STOW-152 | SSTOW-423 | t | AAA2004112026
TOW-16 | STOW-152 | SSTOW-424 | t | AAA2004122026
TOW-16 | STOW-152 | SSTOW-425 | t | AAA2004032026
TOW-16 | STOW-152 | SSTOW-426 | t | AAA2004042026
TOW-16 | STOW-152 | SSTOW-427 | t | AAA2004132026
TOW-16 | STOW-152 | SSTOW-428 | t | AAA2004142026
TOW-16 | STOW-152 | SSTOW-429 | t | AAA2004152026
TOW-16 | STOW-152 | SSTOW-430 | t | AAA2004162026
TOW-16 | STOW-152 | SSTOW-431 | t | AAA2004172026
TOW-16 | STOW-152 | SSTOW-432 | t | AAA2004052026
TOW-16 | STOW-152 | SSTOW-433 | t | AAA2004062026
TOW-16 | STOW-152 | SSTOW-434 | t | AAA2004182026
TOW-16 | STOW-152 | SSTOW-435 | t | AAA2004192026
TOW-16 | STOW-152 | SSTOW-436 | t | AAA2004202026
TOW-16 | STOW-152 | SSTOW-437 | t | AAA2004212026
TOW-16 | STOW-152 | SSTOW-438 | t | AAA2004222026
TOW-16 | STOW-152 | SSTOW-439 | t | AAA2004072026
TOW-16 | STOW-152 | SSTOW-440 | t | AAA2004232026
TOW-16 | STOW-152 | SSTOW-441 | t | AAA2004242026
TOW-16 | STOW-152 | SSTOW-442 | t | AAA2004252026
TOW-16 | STOW-152 | SSTOW-443 | t | AAA2004262026
TOW-16 | STOW-152 | SSTOW-444 | t | AAA2004272026
TOW-16 | STOW-153 | SSTOW-445 | t | AAA2004282026
TOW-17 | STOW-154 | SSTOW-446 | t | AAA9001012026
TOW-17 | STOW-154 | SSTOW-447 | t | AAA9001022026
TOW-17 | STOW-154 | SSTOW-448 | t | AAA9001032026
TOW-17 | STOW-154 | SSTOW-449 | t | AAA9001042026
TOW-17 | STOW-154 | SSTOW-450 | t | AAA9001052026
TOW-17 | STOW-154 | SSTOW-451 | t | AAA9001062026
TOW-17 | STOW-154 | SSTOW-452 | t | AAA9001072026
TOW-17 | STOW-154 | SSTOW-453 | m2 | AAA9001082026
TOW-17 | STOW-154 | SSTOW-454 | m2 | AAA9001092026
TOW-17 | STOW-155 | SSTOW-455 | m3 | AAA90022026
TOW-18 | STOW-156 | SSTOW-456 | - | AAA91012026
TOW-18 | STOW-157 | SSTOW-457 | - | AAA91022026
TOW-18 | STOW-158 | SSTOW-458 | - | AAA91032026
TOW-18 | STOW-159 | SSTOW-459 | - | AAA91042026
TOW-18 | STOW-160 | SSTOW-460 | - | AAA91052026
TOW-18 | STOW-161 | SSTOW-461 | - | AAA91062026
TOW-19 | STOW-162 | SSTOW-462 | - | AAA92012026
TOW-19 | STOW-163 | SSTOW-463 | m3 | AAA92022026
TOW-19 | STOW-164 | SSTOW-464 | - | AAA92042026
TOW-19 | STOW-165 | SSTOW-465 | t | AAA92052026
TOW-19 | STOW-166 | SSTOW-466 | - | AAA9204012026
TOW-20 | STOW-167 | SSTOW-467 | - | AAA92032026
TOW-21 | STOW-168 | SSTOW-468 | - | AAA93012026
TOW-21 | STOW-169 | SSTOW-469 | - | AAA93022026
TOW-21 | STOW-170 | SSTOW-470 | - | AAA93032026
TOW-21 | STOW-171 | SSTOW-471 | - | AAA93042026
TOW-21 | STOW-172 | SSTOW-472 | - | AAA93052026
TOW-22 | STOW-173 | SSTOW-473 | - | AAA9405012026
TOW-22 | STOW-173 | SSTOW-474 | - | AAA9405022026
TOW-22 | STOW-174 | SSTOW-475 | - | AAA9405032026
TOW-22 | STOW-175 | SSTOW-476 | - | AAA9405042026
TOW-22 | STOW-176 | SSTOW-477 | - | AAA9405052026
TOW-22 | STOW-176 | SSTOW-478 | - | AAA9405062026
TOW-22 | STOW-176 | SSTOW-479 | - | AAA9405072026
TOW-22 | STOW-177 | SSTOW-480 | - | AAA9405082026
TOW-22 | STOW-177 | SSTOW-481 | - | AAA9405092026
TOW-22 | STOW-178 | SSTOW-482 | - | AAA9405102026